INITIAL WORK BREAKDOWN STRUCTURE (WBS)

AI-Powered Smart Waste Management System with IoT Integration
for Bope-Poddala Divisional Secretariat

| Project Information | Details |
| --- | --- |
| University | University of Ruhuna |
| Degree / Department | Bachelor of Computer Science - Department of Computer Science |
| Supervisor | Mr Aruna Lorensuhewa |
| Project Period | July 2026 - First week of January 2027 |
| Document | Initial WBS - Version 1.0 |
| Prepared | October 2026 |

Purpose: Decompose the complete project into manageable work packages that can be mapped to Jira Epics/Tasks, sprint plans, responsibilities, deliverables and the project Gantt chart.

# 1. WBS Overview

The WBS is deliverable- and work-package-oriented. Level 1 is the complete project; Level 2 contains 13 major work packages; Level 3 contains the initial work packages used to guide Jira backlog creation, sprint planning, responsibility assignment and scheduling.

| Major Work Package | Primary Accountability | Current Status | Level-3 Items |
| --- | --- | --- | --- |
| 1.0 Project Management | Ravindu / All | In Progress | 8 |
| 2.0 Requirements & Research | All (Ravindu coordinates) | Completed - July 2026 | 11 |
| 3.0 System Design & UI/UX | All (Ravindu coordinates) | In Progress | 11 |
| 4.0 Citizen Mobile App | Ishara | Planned | 8 |
| 5.0 Driver & Collection App | Mahela | Planned | 8 |
| 6.0 Admin Web Dashboard | Mahela | Planned | 10 |
| 7.0 IoT & SmartSort | Ravindu | Planned | 11 |
| 8.0 Waste Prediction AI | Mohommed Rifaa | Planned | 10 |
| 9.0 Route Optimization AI | Chathuranga | Planned | 9 |
| 10.0 Backend & Database | Shared team | Planned | 11 |
| 11.0 System Integration | All (Ravindu coordinates) | Planned | 8 |
| 12.0 Testing & Quality Assurance | All (Ravindu coordinates) | Planned | 9 |
| 13.0 Deployment & Documentation | All (Ravindu coordinates) | Planned | 12 |

# 2. WBS Dictionary - Initial Work Packages

Status reflects the project position at the time of this initial WBS. Primary ownership means accountability/coordination; it does not prevent other team members from contributing.

## 1.0 Project Management

| WBS ID | Work Package | Description / Expected Work | Responsible | Status |
| --- | --- | --- | --- | --- |
| 1.1 | Project Charter | Authorize and summarize project purpose, scope, objectives, stakeholders and governance. | Ravindu | Completed |
| 1.2 | Initial Work Breakdown Structure | Decompose the full project into controlled work packages. | Ravindu | In Progress |
| 1.3 | Project Schedule / Gantt Chart | Build and maintain the time-based project schedule and dependencies. | Chathuranga / Ravindu | Planned |
| 1.4 | Risk Management | Maintain risk register, owners, responses and reviews. | Mohommed Rifaa / Ravindu | Planned |
| 1.5 | Jira Project Management | Maintain epics, backlog, sprints, assignments and progress tracking. | Ravindu | In Progress |
| 1.6 | GitHub & Version Control Management | Maintain repositories, branches, pull requests and collaboration rules. | Ishara / Mahela | Planned |
| 1.7 | Project Documentation Management | Maintain document structure, versions and shared project records. | Ravindu / All | Planned |
| 1.8 | Progress Monitoring & Reporting | Track sprint/project progress and report issues, decisions and milestones. | Ravindu / All | Planned |

## 2.0 Requirements & Research

| WBS ID | Work Package | Description / Expected Work | Responsible | Status |
| --- | --- | --- | --- | --- |
| 2.1 | Stakeholder Analysis | Identify stakeholders, roles, needs and influence. | Ravindu / All | Completed |
| 2.2 | Existing Waste Collection Process Analysis | Study the current collection workflow and operational context. | Mahela | Completed |
| 2.3 | Existing GPS Tracking Investigation | Investigate current truck GPS arrangements and possible integration/data access. | Chathuranga | Completed |
| 2.4 | Citizen Requirements | Gather and analyze citizen-facing functional needs. | Ishara | Completed |
| 2.5 | Driver & Administrator Requirements | Gather operational requirements for collection crews and administrators. | Mahela | Completed |
| 2.6 | IoT / SmartSort Requirements | Define SmartSort prototype, sensing, camera, sorting and communication needs. | Ravindu | Completed |
| 2.7 | Waste Prediction Requirements & Data | Define prediction objectives, inputs, outputs and data requirements. | Mohommed Rifaa | Completed |
| 2.8 | Route Optimization Requirements & Constraints | Define route inputs, operational constraints and expected outputs. | Chathuranga | Completed |
| 2.9 | Functional Requirements | Consolidate required system capabilities. | Ravindu / All | Completed |
| 2.10 | Non-Functional Requirements | Define quality attributes including usability, performance, security and reliability. | Mohommed Rifaa / All | Completed |
| 2.11 | Requirements Review & Validation | Review gathered requirements for completeness and agreement. | All | Completed |

## 3.0 System Design & UI/UX

| WBS ID | Work Package | Description / Expected Work | Responsible | Status |
| --- | --- | --- | --- | --- |
| 3.1 | Overall System Architecture | Define major components, boundaries, interfaces and deployment relationships. | Ravindu / All | In Progress |
| 3.2 | Database & ER Design | Design entities, relationships, keys and spatial/data requirements. | Mahela / All | In Progress |
| 3.3 | Citizen App UI/UX | Design citizen flows, wireframes and Figma screens. | Ishara | In Progress |
| 3.4 | Driver App UI/UX | Design driver collection and route workflows in Figma. | Mahela | In Progress |
| 3.5 | Admin Dashboard UI/UX | Design administrative monitoring and management screens. | Mahela | In Progress |
| 3.6 | IoT SmartSort Architecture | Design hardware, sensing, camera, actuation and MQTT data flow. | Ravindu | In Progress |
| 3.7 | Waste Prediction AI Architecture | Design prediction pipeline, data flow, model service and evaluation approach. | Mohommed Rifaa | In Progress |
| 3.8 | Route Optimization AI Architecture | Design optimization inputs, algorithm/service flow and evaluation approach. | Chathuranga | In Progress |
| 3.9 | Backend API Architecture | Define service modules, API boundaries, authentication and integration patterns. | Shared team | Planned |
| 3.10 | System Integration Architecture | Define interfaces among apps, backend, IoT, AI, maps and GPS. | Chathuranga / Ravindu | Planned |
| 3.11 | Design Review & Validation | Review architecture and designs before major implementation. | All | Planned |

## 4.0 Citizen Mobile App

| WBS ID | Work Package | Description / Expected Work | Responsible | Status |
| --- | --- | --- | --- | --- |
| 4.1 | Authentication & User Profile | Implement citizen registration/login and profile functions. | Ishara | Planned |
| 4.2 | Citizen Dashboard | Implement main citizen navigation and summary view. | Ishara | Planned |
| 4.3 | Collection Schedule | Display relevant upcoming collection dates/types from backend. | Ishara | Planned |
| 4.4 | Complaints & Requests | Create, submit and track citizen complaints/requests. | Ishara | Planned |
| 4.5 | Notifications | Deliver collection and service notifications. | Ishara | Planned |
| 4.6 | Waste Sorting / Disposal Guide | Provide citizen guidance on waste categories/disposal. | Ishara | Planned |
| 4.7 | Backend Integration | Connect citizen features to authenticated backend APIs. | Ishara / Shared team | Planned |
| 4.8 | Citizen App Testing | Verify citizen workflows, errors and integration behavior. | Ishara / All | Planned |

## 5.0 Driver & Collection App

| WBS ID | Work Package | Description / Expected Work | Responsible | Status |
| --- | --- | --- | --- | --- |
| 5.1 | Driver Authentication | Implement secure driver access. | Mahela | Planned |
| 5.2 | Assigned Collection Tasks | Display assigned collection work and relevant details. | Mahela | Planned |
| 5.3 | Route Map & Navigation | Present optimized/assigned route information on maps. | Mahela / Chathuranga | Planned |
| 5.4 | GPS / Location Handling | Capture/use permitted location data for collection operations. | Mahela / Chathuranga | Planned |
| 5.5 | Collection Start / Completion | Record collection execution status and completion. | Mahela | Planned |
| 5.6 | Collection History | Provide previous collection records/history. | Mahela | Planned |
| 5.7 | Backend Integration | Connect driver workflows to backend services. | Mahela / Shared team | Planned |
| 5.8 | Driver App Testing | Verify collection workflows, map/GPS behavior and integration. | Mahela / All | Planned |

## 6.0 Admin Web Dashboard

| WBS ID | Work Package | Description / Expected Work | Responsible | Status |
| --- | --- | --- | --- | --- |
| 6.1 | Admin Authentication | Implement secure administrative access. | Mahela | Planned |
| 6.2 | Dashboard Overview | Provide operational summary, alerts and key metrics. | Mahela | Planned |
| 6.3 | Live Vehicle / GPS Monitoring | Display available/authorized vehicle location information. | Mahela / Chathuranga | Planned |
| 6.4 | SmartSort Monitoring | Display device status, fill levels and SmartSort information. | Mahela / Ravindu | Planned |
| 6.5 | Complaint Management | Review and manage citizen complaints/requests. | Mahela | Planned |
| 6.6 | Collection Schedule Management | Create/update collection schedules. | Mahela | Planned |
| 6.7 | Route Management | Review/manage generated and assigned routes. | Mahela / Chathuranga | Planned |
| 6.8 | User Management | Manage relevant system users and roles. | Mahela | Planned |
| 6.9 | Reports & Analytics | Present operational reports and AI-supported analytics. | Mahela / AI owners | Planned |
| 6.10 | Admin Dashboard Testing | Verify dashboard workflows, permissions and integration. | Mahela / All | Planned |

## 7.0 IoT & SmartSort

| WBS ID | Work Package | Description / Expected Work | Responsible | Status |
| --- | --- | --- | --- | --- |
| 7.1 | Hardware Design | Define prototype components, wiring, power and physical mechanism. | Ravindu | Planned |
| 7.2 | ESP32 / ESP32-CAM Setup | Configure microcontroller/camera hardware and firmware base. | Ravindu | Planned |
| 7.3 | Camera Integration | Capture controlled single-item waste images. | Ravindu | Planned |
| 7.4 | Waste Image Capture | Prepare image-transfer/classification request workflow. | Ravindu / Rifaa | Planned |
| 7.5 | Servo Sorting Mechanism | Implement controlled flap/chute actuation for supported categories. | Ravindu | Planned |
| 7.6 | Ultrasonic Fill-Level Monitoring | Measure compartment fill levels. | Ravindu | Planned |
| 7.7 | MQTT Communication | Publish device, fill and classification-related data. | Ravindu / Shared team | Planned |
| 7.8 | Device Status Monitoring | Report online/offline/error and operational state. | Ravindu | Planned |
| 7.9 | AI Classification Integration | Connect image capture to server-side classification and sorting result. | Ravindu / Rifaa | Planned |
| 7.10 | SmartSort Prototype Assembly | Assemble public-station prototype for demonstration. | Ravindu / All | Planned |
| 7.11 | Hardware & IoT Testing | Test sensors, camera, actuation, messaging and failure conditions. | Ravindu / All | Planned |

## 8.0 Waste Prediction AI

| WBS ID | Work Package | Description / Expected Work | Responsible | Status |
| --- | --- | --- | --- | --- |
| 8.1 | Data Collection | Acquire available historical/operational data suitable for prediction. | Mohommed Rifaa | Planned |
| 8.2 | Data Cleaning & Preparation | Clean, transform and structure prediction data. | Mohommed Rifaa | Planned |
| 8.3 | Exploratory Data Analysis | Analyze patterns, missingness, seasonality and candidate relationships. | Mohommed Rifaa | Planned |
| 8.4 | Feature Engineering | Create useful model inputs from available data. | Mohommed Rifaa | Planned |
| 8.5 | Model Development | Select and implement candidate prediction approaches. | Mohommed Rifaa | Planned |
| 8.6 | Model Training | Train/tune candidate models. | Mohommed Rifaa | Planned |
| 8.7 | Model Evaluation | Evaluate using suitable metrics and validation strategy. | Mohommed Rifaa | Planned |
| 8.8 | Prediction API | Expose selected model through a Python/FastAPI service. | Mohommed Rifaa | Planned |
| 8.9 | Backend / Dashboard Integration | Connect predictions to core system and administrative views. | Mohommed Rifaa / Shared team | Planned |
| 8.10 | Prediction Module Testing | Test model service, edge cases and integrated outputs. | Mohommed Rifaa / All | Planned |

## 9.0 Route Optimization AI

| WBS ID | Work Package | Description / Expected Work | Responsible | Status |
| --- | --- | --- | --- | --- |
| 9.1 | Collection Point Data Preparation | Prepare locations and operational attributes for routing. | Chathuranga | Planned |
| 9.2 | Route Constraints Definition | Formalize vehicle, capacity, priority, timing and route constraints as applicable. | Chathuranga | Planned |
| 9.3 | Optimization Algorithm Development | Implement candidate route optimization logic. | Chathuranga | Planned |
| 9.4 | GPS / Map Data Integration | Integrate map/location inputs needed for routing. | Chathuranga | Planned |
| 9.5 | Route Optimization API | Expose optimization capability as a service/API. | Chathuranga | Planned |
| 9.6 | Driver App Integration | Provide optimized/assigned route output to driver workflows. | Chathuranga / Mahela | Planned |
| 9.7 | Admin Dashboard Integration | Provide route planning/monitoring outputs to administrators. | Chathuranga / Mahela | Planned |
| 9.8 | Algorithm Evaluation | Evaluate route quality, feasibility and performance on test scenarios. | Chathuranga | Planned |
| 9.9 | Route Optimization Testing | Test service, constraints, errors and integrated route use. | Chathuranga / All | Planned |

## 10.0 Backend & Database

| WBS ID | Work Package | Description / Expected Work | Responsible | Status |
| --- | --- | --- | --- | --- |
| 10.1 | Spring Boot Project Setup | Create modular backend foundation and environment configuration. | Shared team | Planned |
| 10.2 | Database Implementation | Implement PostgreSQL/PostGIS schema, migrations and spatial/data structures. | Shared team | Planned |
| 10.3 | Authentication & Authorization | Implement user authentication and role-based authorization. | Shared team | Planned |
| 10.4 | Citizen APIs | Implement APIs supporting citizen workflows. | Shared team / Ishara | Planned |
| 10.5 | Driver APIs | Implement APIs supporting driver/collection workflows. | Shared team / Mahela | Planned |
| 10.6 | Admin APIs | Implement administrative and reporting APIs. | Shared team / Mahela | Planned |
| 10.7 | IoT / MQTT Integration | Consume/store IoT data and support device interactions. | Shared team / Ravindu | Planned |
| 10.8 | AI Service Integration | Connect backend to prediction and optimization services. | Shared team / AI owners | Planned |
| 10.9 | GPS / Map Integration | Support authorized GPS/map/location data workflows. | Shared team / Chathuranga | Planned |
| 10.10 | API Documentation | Maintain Swagger/OpenAPI and integration guidance. | Shared team | Planned |
| 10.11 | Backend Testing | Test APIs, validation, authorization and persistence. | Shared team / All | Planned |

## 11.0 System Integration

| WBS ID | Work Package | Description / Expected Work | Responsible | Status |
| --- | --- | --- | --- | --- |
| 11.1 | Citizen App Integration | Integrate citizen app with production-like backend flows. | Ishara / Shared team | Planned |
| 11.2 | Driver App Integration | Integrate driver app with backend, maps and route services. | Mahela / Shared team | Planned |
| 11.3 | Admin Dashboard Integration | Integrate dashboard with backend, IoT, GPS and AI data. | Mahela / Shared team | Planned |
| 11.4 | IoT Integration | Connect SmartSort MQTT/device data end-to-end. | Ravindu / Shared team | Planned |
| 11.5 | Waste Prediction Integration | Connect prediction service to system workflows. | Rifaa / Shared team | Planned |
| 11.6 | Route Optimization Integration | Connect route service to driver/admin workflows. | Chathuranga / Shared team | Planned |
| 11.7 | GPS Integration / Prototype | Integrate authorized provider data or demonstrate agreed academic fallback. | Chathuranga / Shared team | Planned |
| 11.8 | End-to-End Integration | Validate complete cross-module data and user flows. | All | Planned |

## 12.0 Testing & Quality Assurance

| WBS ID | Work Package | Description / Expected Work | Responsible | Status |
| --- | --- | --- | --- | --- |
| 12.1 | Test Planning | Define test strategy, cases, responsibilities and evidence. | All | Planned |
| 12.2 | Unit Testing | Test components/functions within each module. | All | Planned |
| 12.3 | Integration Testing | Test module/API/device/service interfaces. | All | Planned |
| 12.4 | System Testing | Test complete system against requirements. | All | Planned |
| 12.5 | Usability Testing | Evaluate key user workflows and interface usability. | All | Planned |
| 12.6 | Performance Testing | Evaluate selected response-time/load/resource behaviors. | All | Planned |
| 12.7 | Security Testing | Verify authentication, authorization and common security controls. | All | Planned |
| 12.8 | Defect Tracking & Fixing | Record, prioritize, fix and retest defects. | All | Planned |
| 12.9 | User Acceptance / Stakeholder Validation | Validate prototype with relevant stakeholders where feasible. | All | Planned |

## 13.0 Deployment & Documentation

| WBS ID | Work Package | Description / Expected Work | Responsible | Status |
| --- | --- | --- | --- | --- |
| 13.1 | Deployment Environment | Prepare deployment/demo environment and configuration. | All | Planned |
| 13.2 | Application Deployment | Deploy mobile/web/backend components for demonstration. | All | Planned |
| 13.3 | Database Deployment | Deploy/configure database and required data. | Shared team | Planned |
| 13.4 | AI Service Deployment | Deploy prediction and route services. | Rifaa / Chathuranga | Planned |
| 13.5 | IoT Demonstration Setup | Prepare SmartSort hardware and connectivity for final demonstration. | Ravindu / All | Planned |
| 13.6 | Software Requirements Specification (SRS) | Prepare and maintain formal SRS from validated requirements. | All (Ravindu coordinates) | Planned |
| 13.7 | System Design Documentation | Document architecture, database, interfaces and module designs. | All | Planned |
| 13.8 | Technical Documentation | Document setup, APIs, code structure, hardware and deployment. | All | Planned |
| 13.9 | User Documentation | Prepare usage guidance for relevant system roles. | All | Planned |
| 13.10 | Final Project Report | Compile final academic project report and evidence. | All | Planned |
| 13.11 | Final Presentation | Prepare final presentation materials. | All | Planned |
| 13.12 | Final Demonstration | Prepare and conduct integrated project demonstration. | All | Planned |

# 3. WBS-to-Project-Management Mapping

| Artifact | Relationship to WBS |
| --- | --- |
| WBS | Defines what work exists and how it is decomposed. |
| Jira Epic | Represents a major module/workstream corresponding broadly to Level-2 WBS areas. |
| Jira Story / Task | Represents implementable or manageable work derived from Level-3 packages. |
| Jira Subtask | Represents a smaller unit needed to complete a Story/Task. |
| Sprint | Defines when selected Jira work is planned and executed. |
| Gantt Chart | Shows project calendar, durations, dependencies and major milestones derived from the WBS. |
| GitHub / Test Evidence | Provides implementation, review and verification evidence for technical work. |

# 4. WBS Control Notes

Requirements & Research (2.0) is recorded as completed in July 2026.

Project Management (1.0) and System Design & UI/UX (3.0) are the current focus as of October 2026.

SmartSort is a limited prototype/public-station concept, not a household-wide deployment.

GPS work must first investigate authorized access to the existing tracking provider; an independent prototype is a fallback for academic demonstration.

Backend & Database is explicit in the WBS because it is substantial shared work even if Jira ownership is distributed across the team.

This is an initial WBS and should be baselined after team/supervisor review. New detail may be added beneath Level-3 packages without changing the project purpose or scope.