## Risk Register
EcoCollect – Project Risk Register
AI-Powered Smart Waste Management System ¦ Baseline: October 2026
Risk ID | Category | Risk Description | Cause / Trigger | Potential Impact | Likelihood (1-5) | Impact (1-5) | Risk Score | Risk Level | Risk Owner | Mitigation / Preventive Action | Contingency / Response | Status | Review Date
R-01 | External Integration | Authorized GPS provider API/data may not be available. | Provider restrictions or permission delays. | Production GPS integration may not be completed. | 4 | 4 | 16 | High | Ravindu Nadeesha | Investigate authorization early; document interface requirements. | Use an independent academic GPS prototype. | Open | 2026-10-31
R-02 | AI / Data | Waste data may be insufficient or low quality. | Missing/inconsistent records or limited history. | Prediction quality may be limited. | 4 | 5 | 20 | Critical | Mohommed Rifaa | Profile, clean and validate data early; establish baseline models. | Use the best defensible model and document limitations. | Open | 2026-10-31
R-03 | AI / IoT | SmartSort may misclassify waste items. | Limited dataset, lighting variation or unsupported items. | Incorrect compartment selection. | 4 | 4 | 16 | High | Ravindu Nadeesha | Controlled lighting, fixed camera, representative data and confidence threshold. | Use Unknown/Reject handling for low confidence. | Open | 2026-10-31
R-04 | Hardware | ESP32/camera/sensors/servo may fail or be unavailable. | Defects, procurement delay, unstable power or wiring. | SmartSort development/demo may be delayed. | 3 | 4 | 12 | High | Ravindu Nadeesha | Procure early; use common parts; bench-test modules independently. | Keep spare critical parts and demonstration evidence. | Open | 2026-10-31
R-05 | Integration | System modules may not integrate smoothly. | Unclear contracts, inconsistent payloads or late integration. | End-to-end prototype may be unstable. | 4 | 5 | 20 | Critical | Ravindu Nadeesha | Define REST/MQTT contracts early and integrate incrementally. | Freeze interfaces and prioritize core workflows. | Open | 2026-10-31
R-06 | Schedule | Development may slip beyond 31 December 2026. | Underestimation, dependencies, defects or scope growth. | January preparation time may be lost. | 4 | 5 | 20 | Critical | Ravindu Nadeesha | Track milestones weekly; parallelize work; protect core scope. | Drop optional features and stabilize core demonstration. | Open | 2026-10-31
R-07 | Team | Workload/knowledge may become concentrated in one member. | Uneven tasks, absences or siloed ownership. | Bottlenecks and single-person dependency. | 3 | 4 | 12 | High | Ravindu Nadeesha | Cross-review and share integration/testing/documentation. | Reassign Jira work and pair members on critical modules. | Open | 2026-10-31
R-08 | Infrastructure | Network instability may interrupt communication. | Weak Wi-Fi, configuration or service downtime. | Telemetry/classification/app operations may fail. | 3 | 3 | 9 | Medium | Ravindu Nadeesha | Test demo network and implement timeout/error states. | Use controlled local network/demo configuration. | Open | 2026-10-31
R-09 | Security | Secrets or user data may be exposed. | Secrets in Git, weak authorization or validation. | Security/data exposure risk. | 3 | 5 | 15 | High | Mahela Yapa | Use .env, JWT authorization, password hashing, validation and review. | Rotate secrets, patch endpoints and retest. | Open | 2026-10-31
R-10 | Stakeholder | Stakeholders may be unavailable for validation. | Scheduling conflicts or delayed responses. | Decisions may be delayed or assumption-based. | 3 | 3 | 9 | Medium | Ravindu Nadeesha | Request focused reviews early and record assumptions. | Proceed with documented supervisor/team-approved assumptions. | Open | 2026-10-31
R-11 | Scope | Scope creep may exceed available time/resources. | New ideas or production-level expectations. | Core quality and deadline threatened. | 4 | 4 | 16 | High | Ravindu Nadeesha | Baseline WBS/SRS and use change control. | Move non-essential work to Future Enhancements. | Open | 2026-10-31
R-12 | Deployment | Deployment/configuration may fail. | Environment differences, migrations or port conflicts. | System may not be reproducible for demo. | 3 | 5 | 15 | High | Mahela Yapa | Build Docker Compose early and document setup/migrations. | Maintain a tested local demo environment and backup. | Open | 2026-10-31
R-13 | Quality | Insufficient testing may leave critical defects. | Testing deferred too late or incomplete cases. | Failures during evaluation. | 4 | 5 | 20 | Critical | Ravindu Nadeesha | Test continuously and reserve December for system QA. | Freeze features and prioritize critical defect regression. | Open | 2026-10-31
R-14 | Version Control | Git conflicts or poor branch practices may disrupt work. | Direct main changes or large unreviewed merges. | Lost work and integration delays. | 3 | 4 | 12 | High | Ishara Edirisinghe | Use feature branches, PRs, reviews and Jira-linked commits. | Revert/recover from Git history and resolve before merge. | Open | 2026-10-31
R-15 | Presentation | Final demonstration may fail. | Hardware/network/service/data dependency failures. | Completed work may not be demonstrated effectively. | 3 | 5 | 15 | High | Ravindu Nadeesha | Rehearse stable demo; verify services; capture evidence. | Use prepared screenshots/video/fallback material. | Open | 2026-10-31
R-16 | AI / Route | Route optimization may be overcomplicated too early. | Too many constraints before stable baseline. | Algorithm/integration delay. | 3 | 4 | 12 | High | Chathuranga Gayashan | Implement distance-minimizing baseline first. | Return to stable baseline for final prototype. | Open | 2026-10-31
R-17 | AI / Vision | Vision dataset may not represent local waste. | Small/imbalanced/non-local dataset. | Physical prototype accuracy may be poor. | 4 | 4 | 16 | High | Ravindu Nadeesha | Collect representative local images and separate train/validation/test. | Narrow supported examples and report limitations. | Open | 2026-10-31
R-18 | Database / Geospatial | Poor coordinates/CRS may affect maps and routes. | Invalid coordinates or inconsistent CRS. | Wrong locations/distances and misleading routes. | 3 | 4 | 12 | High | Mahela Yapa | Standardize CRS and validate collection points. | Correct invalid points and use verified demo data. | Open | 2026-10-31

## Risk Summary
EcoCollect – Risk Summary
Risk Level | Count | Status | Count
Critical | 4 | Open | 18
High | 12 | Monitoring | 0
Medium | 2 | Mitigated | 0
Low | 0 | Closed | 0
|  | Accepted | 0
Metric | Value
Total Risks | 18
Average Score | 14.8333
Highest Score | 20
Critical + High | 16

## Scoring Guide
EcoCollect – Risk Scoring Guide
Likelihood | Definition
1 – Rare | Very unlikely during the project.
2 – Unlikely | Could occur, but not expected.
3 – Possible | May occur during the project.
4 – Likely | Expected unless actively managed.
5 – Almost Certain | Highly likely or already showing warning signs.
Impact | Definition
1 – Insignificant | Minimal effect; easily corrected.
2 – Minor | Small delay/rework; core objectives unaffected.
3 – Moderate | Noticeable schedule/quality impact.
4 – Major | Threatens a major module, milestone or demo capability.
5 – Severe | Threatens completion, core objectives or final evaluation.
Risk Score | Level
1–5 | Low
6–11 | Medium
12–19 | High
20–25 | Critical
Formula | Risk Score = Likelihood × Impact
Review Practice | Review open/high/critical risks during sprint/project reviews and update them when circumstances change.